## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Requisite
1 | Git Repository |  |  | Darshan | 2023-06-30 | Closed
Implementation
1 | Wire Frames |  |  | Vaishnavi | 2023-06-30 | Closed
2 | Logo Design |  |  | Dipak | 2023-06-30 | Closed
3 | Angular Project Creation |  |  | Dipak | 2023-06-30 | Closed
4 | DataBase Hosted on MsSql |  |  | Darshan | 2023-07-01 | Closed
5 | Scaffolding of DataBase |  |  | Darshan | 2023-07-01 | Closed
6 | Employee Rest Api |  |  | Darshan | 2023-07-01 | Closed
7 | Stores Rest Api |  |  | Roshan | 2023-07-01 | Closed
8 | Authors Rest Api |  |  | Parth | 2023-07-01 | Closed
9 | Titles Rest Api |  |  | Dipak | 2023-07-01 | Closed
10 | Publishers Rest Api |  |  | Vaishnavi | 2023-07-01 | Closed
11 | Jobs Rest Api |  |  | Suyog | 2023-07-01 | Closed
12 | Sales Rest Api |  |  | Prashant | 2023-07-01 | Closed
13 | Login Page UI (Template in HTML CSS) |  |  | Dipak | 02107-2023 | Closed
14 | Publisher Signup Page UI (Template in HTML CSS) |  |  | Dipak | 2023-07-02 | Closed
15 | Author Signup Page UI (Template in HTML CSS) |  |  | Dipak | 2023-07-03 | Closed
16 | Login API |  |  | Darshan | 2023-07-02 | Closed
17 | Sign up Api |  |  | Darshan | 2023-07-02 | Closed
18 | HomePage (Dashboard) UI |  |  | Parth | 2023-07-02 | Closed
19 | (Login & Register) UI & Intgration with API |  |  | Darshan | 2023-07-04 | closed
20 | Publisher Dashboard UI & Integration with API |  |  | Dipak | 2023-07-06 | WIP
21 | Author Dashboard UI & Integration with API |  |  | Dipak | 2023-07-06 | WIP
22 | Profile Page for Author and Publisher UI |  |  | Parth | 2023-07-06 | WIP
23 | Title Publish Request UI |  |  | Dipak | o6-07-2023 | WIP
| QA |  |  | Roshan | 2023-07-03 | Closed
1 | Login Module Testing |  |  | Prashant | 2023-07-03 | Closed
2 | Sign up Module Testing |  |  | Vedant | 2023-07-03 | WIP
3 | Home Screen Testing |  |  | Vedant | 2023-07-04 | Open
4 | Employees Module Testing |  |  | Vedant | 2023-07-05 | Open
5 | Jobs Module Testing |  |  | Vedant | 2023-07-06 | Open
6 | Authors Module Testing |  |  | Suyog | 2023-07-03 | Open
7 | Publishers Module Testing |  |  | Vaishnavi | 2023-07-03 | Open
8 | Stores Module Testing |  |  | Parth | 2023-07-03 | Open
9 | Titles Module Testing |  |  | Dipak | 2023-07-03 | Open
Release Setup - Cloud Infra
1 | Azure App Service Web API Application |  |  | Roshan | 2023-07-05 | Open
2 | Azure App Service Angular Application |  |  | Roshan | 2023-07-05 | Open
3 | Azure Storage Account and Blob Storage |  |  | Vedant | 2023-07-05 | Open
4 | Azure Logic App |  |  | Vaishnavi | 2023-07-05 | Open
5 | Azure Function App |  |  | Vaishnavi | 2023-07-05 | Open
Deployment
1 | Deployment Strategy |  |  | All Members | 2023-07-05 | Open
2 | Setup for deployment - Angular App |  |  | Dipak | 2023-07-03 | Open
3 | Setup for deployment - API |  |  | Dipak | 2023-07-03 | Open
4 | Setup - Dependendat Resources |  | DB, Logic app etc | Dipak | 2023-07-04 | Open
5 | Test APP |  |  | Prashant | 2023-07-05 | Open
6 | Test API |  |  | Vedant | 2023-07-06 | Open
7 | Test Other Resources |  |  | Roshan | 2023-07-07 | Open