## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Req
1 | Git Repository |  |  | Darshan | 2023-06-30 | Closed
Implementation
1 | Logo Design |  |  | Dipak | 2023-06-30 | Closed
2 | Angular Project Creation |  |  | Dipak | 2023-06-30 | Closed
3 | Dashboard |  |  | Parth | 2023-07-01 | WIP
5 | DataBase Hosted on MsSql |  |  | Darshan | 2023-07-01 | Closed
6 | Scaffolding of DataBase |  |  | Parth | 2023-07-01 | Closed
7 | Employee Rest Api |  |  | Darshan | 2023-07-01 | Closed
8 | Stores Rest Api |  |  | Roshan | 2023-07-01 | Closed
9 | Authors Rest Api |  |  | Parth | 2023-07-01 | Closed
10 | Titles Rest Api |  |  | Dipak | 2023-07-01 | Closed
11 | Publishers Rest Api |  |  | Vaishnavi | 2023-07-01 | Closed
12 | Jobs Rest Api |  |  | Suyog | 2023-07-01 | Closed
13 | Sales Rest Api |  |  | Prashant | 2023-07-01 | Closed
14 | Login API |  |  | Darshan | 2023-07-02 | Closed
15 | Sign up Api |  |  | Darshan | 2023-07-02 | Closed
QA
1 | Login Module Testing |  |  | Prashant | 2023-07-03 | WIP
2 | Sign up Module Testing |  |  | Vedant | 2023-07-03 | WIP
3 | Authors Api Testing |  |  | Suyog | 2023-07-03 | WIP
4 | Publishers Api Testing |  |  | Vaishnavi | 2023-07-03 | WIP
5 | Stores Api Testing |  |  | Parth | 2023-07-03 | WIP
6 | Titles Api Testing |  |  | Dipak | 2023-07-03 | WIP
7 | Employees Api Testing |  |  | Roshan | 2023-07-03 | WIP
Release Setup
1 | Azure App Service Web API Application |  |  | Roshan | 2023-07-05 | Open
2 | Azure App Service Angular Application |  |  | Roshan | 2023-07-05 | Open
3 | Azure Storage Account and Blob Storage |  |  | Vedant | 2023-07-05 | Open
4 | Azure Logic App |  |  | Vaishnavi | 2023-07-05 | Open
5 | Azure Function App |  |  | Vaishnavi | 2023-07-05 | Open
Deployment